## 📋 Dashboard
MCHD — Device Upgrade Master Workbook
Comprehensive planning reference — Station Groups · Tower Sites · Controller Inventory
SECTION 1 — EMS Station Groups (Device Upgrade Planning)
Group | Stations | Area | Visit Order | Sheet Tab
Group 1 | 7 stations | North Conroe / Willis | St.10→15→11→14→45→16→13 | Group 1
Group 2 | 8 stations | Woodlands / Spring / Shenandoah | St.27→24→23→26→20→25→22→21 | Group 2
Group 3 | 7 stations | East / Porter / Splendora | St.12→33→32→35→30→34→31 | Group 3
Group 4 | 7 stations | West / Magnolia / Montgomery | St.44→43→47→46→40→41→42 | Group 4
SECTION 2 — Tower Sites
Tower Name | Address | Sheet Tab
Conroe Service Center Tower | 1400 South Loop 336 W, Conroe | Tower Sites
East County / Splendora Tower | 14809 First St, Splendora | Tower Sites
Thompson Road Tower | 12370 Thompson Rd, Willis | Tower Sites
Robinson Rd Tower | 27906 Robinson Rd, Spring | Tower Sites
Magnolia Tower | 14575 FM 1488, Magnolia | Tower Sites
Grangerland Tower | 13885 Grangerland Rd, Conroe | Tower Sites
Conroe Service Tower | 401 Sgt Ed Holcomb Blvd, Conroe | Tower Sites
SECTION 3 — Controller Inventory Summary
Status | Count | Notes
✅ Has 1502 Board (SSP/D2) | 20 units | No hardware replacement needed
🔴 Needs 1502 Replacement (DCtrl) | 15 units | DController → must swap to 1502 board
🟡 Other Types — Review Required | 5 units | PIM400-1501 (×4), SSP-LX (×1) — review
Total Controllers | 40 units | Across all sites per 8/21/2025 report

## Summary Overview
MCHD EMS — Device Upgrade Schedule by Station Group
28 Stations · 4 Groups of 7 · Grouped geographically for efficient routing
Group | # Stations | Area Covered | Stations Included | Approx. Drive Coverage | Suggested Visit Order | Status
1 | 7 | North Conroe / Willis | St. 10, 11, 13, 14, 15, 16, 45 | ~15 mi radius | 10 → 15 → 11 → 14 → 45 → 16 → 13
2 | 8 | Woodlands / Spring / Shenandoah | St. 20, 21, 22, 23, 24, 25, 26, 27 | ~12 mi radius | 27 → 24 → 23 → 26 → 20 → 25 → 22 → 21
3 | 7 | East / Porter / Splendora | St. 12, 30, 31, 32, 33, 34, 35 | ~20 mi radius | 12 → 33 → 32 → 35 → 30 → 34 → 31
4 | 7 | West / Magnolia / Montgomery | St. 40, 41, 42, 43, 44, 46, 47 | ~20 mi radius | 44 → 43 → 47 → 46 → 40 → 41 → 42
Tower Start Date: | 2026-05-04
EMS Station Start Date: | 2026-05-04
Tower estimated completion date: | 2026-07-01
EMS Station estimated completion date: | 2026-06-30

## Group 1
Group 1 — North Conroe / Willis
Suggested Visit Order: St.10 → St.15 → St.11 → St.14 → St.45 → St.16 → St.13
Station | Address | City | ZIP | Latitude | Longitude | Notes / Contacts | Device Upgrade Status | Date Completed | Tech Initials
St. 10 | 2920 N Loop 336 E | Conroe | 77305 | 30.3305 | -95.408 |  | Pending
St. 11 | 1300 S Loop 336 W | Conroe | 77304 | 30.2841 | -95.4767 |  | Pending
St. 13 | 200 S Kennedy | Willis | 77378 | 30.421 | -95.4861 |  | Pending
St. 14 | 1818 League Line Rd | Panorama Village | 77304 | 30.3703 | -95.4984 |  | Pending
St. 15 | 811 W Semands Ave | Conroe | 77301 | 30.3238 | -95.466 |  | Pending
St. 16 | 11111 Calvary Rd | Willis | 77318 | 30.4614 | -95.5194 |  | Pending
St. 45 | 14344 Hwy 105 W | Conroe | 77304 | 30.353 | -95.5787 |  | Pending
Total: 7 Stations |  | 0 of 7 Completed

## Group 2
Group 2 — Woodlands / Spring / Shenandoah
Suggested Visit Order: St.27 → St.24 → St.23 → St.26 → St.20 → St.25 → St.22 → St.21
Station | Address | City | ZIP | Latitude | Longitude | Notes / Contacts | Device Upgrade Status | Date Completed | Tech Initials
St. 20 | 250 Harpers Landing Blvd | Conroe | 77385 | 30.2139 | -95.4531 |  | Pending
St. 21 | 28830 Birnham Woods Dr | Spring | 77386 | 30.118 | -95.3837 |  | Pending
St. 22 | 335 Volunteer Dr | Spring | 77380 | 30.1283 | -95.4481 |  | Pending
St. 23 | 9303 Gosling Rd | Spring | 77381 | 30.183 | -95.4925 |  | Pending
St. 24 | 8001 McBeth Way | The Woodlands | 77381 | 30.1813 | -95.5592 |  | Pending
St. 25 | 9951 Grogans Mill Rd | The Woodlands | 77380 | 30.1613 | -95.4706 |  | Pending
St. 26 | 29915 I-45 | Shenandoah | 77381 | 30.1794 | -95.4624 |  | Pending
St. 27 | 5918 FM 1488 | Magnolia | 77354 | 30.2247 | -95.5578 |  | Pending
Total: 8 Stations |  | 0 of 8 Completed

## Group 3
Group 3 — East / Porter / Splendora
Suggested Visit Order: St.12 → St.33 → St.32 → St.35 → St.30 → St.34 → St.31
Station | Address | City | ZIP | Latitude | Longitude | Notes / Contacts | Device Upgrade Status | Date Completed | Tech Initials
St. 12 | 14421 Hwy 105 E | Cut-N-Shoot | 77306 | 30.3324 | -95.3489 |  | Pending
St. 30 | 21084 Loop 494 | New Caney | 77357 | 30.1404 | -95.2166 |  | Pending
St. 31 | 14809 First St | Splendora | 77372 | 30.2292 | -95.1645 |  | Pending
St. 32 | 14596 FM 1314 | Conroe | 77302 | 30.2399 | -95.3819 |  | Pending
St. 33 | 16723 FM 2090 | Conroe | 77306 | 30.2564 | -95.3157 |  | Pending
St. 34 | 23550 Loop 494 | Porter | 77365 | 30.1058 | -95.2291 |  | Pending
St. 35 | 20515 FM 1314 | Porter | 77365 | 30.1527 | -95.3036 |  | Pending
Total: 7 Stations |  | 0 of 7 Completed

## Group 4
Group 4 — West / Magnolia / Montgomery
Suggested Visit Order: St.44 → St.43 → St.47 → St.46 → St.40 → St.41 → St.42
Station | Address | City | ZIP | Latitude | Longitude | Notes / Contacts | Device Upgrade Status | Date Completed | Tech Initials
St. 40 | 14575 FM 1488 | Magnolia | 77354 | 30.2278 | -95.6934 |  | Pending
St. 41 | 12527 Patridge Cir | Pinehurst | 77362 | 30.1491 | -95.6624 |  | Pending
St. 42 | 26555 Nichols Sawmill Rd | Magnolia | 77355 | 30.1333 | -95.7534 |  | Pending
St. 43 | 18960 Freeport Dr | Montgomery | 77356 | 30.3861 | -95.6619 |  | Pending
St. 44 | 18294 FM 1097 | Montgomery | 77356 | 30.4376 | -95.6367 |  | Pending
St. 46 | 2615 Woodforest Pkwy N | Montgomery | 77316 | 30.2826 | -95.5674 |  | Pending
St. 47 | 19530 Keenan Cut-Off Rd | Montgomery | 77316 | 30.3253 | -95.6678 |  | Pending
Total: 7 Stations |  | 0 of 7 Completed

## All Stations Master
MCHD EMS — All 29 Stations Master List
Group | Station | Address | City | ZIP | Latitude | Longitude | Notes | Upgrade Status | Date Completed
Group 1 | St. 10 | 2920 N Loop 336 E | Conroe | 77305 | 30.3305 | -95.408 |  | Pending
Group 1 | St. 11 | 1300 S Loop 336 W | Conroe | 77304 | 30.2841 | -95.4767 |  | Pending
Group 1 | St. 13 | 200 S Kennedy | Willis | 77378 | 30.421 | -95.4861 |  | Pending
Group 1 | St. 14 | 1818 League Line Rd | Panorama Village | 77304 | 30.3703 | -95.4984 |  | Pending
Group 1 | St. 15 | 811 W Semands Ave | Conroe | 77301 | 30.3238 | -95.466 |  | Pending
Group 1 | St. 16 | 11111 Calvary Rd | Willis | 77318 | 30.4614 | -95.5194 |  | Pending
Group 1 | St. 45 | 14344 Hwy 105 W | Conroe | 77304 | 30.353 | -95.5787 |  | Pending
Group 2 | St. 20 | 250 Harpers Landing Blvd | Conroe | 77385 | 30.2139 | -95.4531 |  | Pending
Group 2 | St. 21 | 28830 Birnham Woods Dr | Spring | 77386 | 30.118 | -95.3837 |  | Pending
Group 2 | St. 22 | 335 Volunteer Dr | Spring | 77380 | 30.1283 | -95.4481 |  | Pending
Group 2 | St. 23 | 9303 Gosling Rd | Spring | 77381 | 30.183 | -95.4925 |  | Pending
Group 2 | St. 24 | 8001 McBeth Way | The Woodlands | 77381 | 30.1813 | -95.5592 |  | Pending
Group 2 | St. 25 | 9951 Grogans Mill Rd | The Woodlands | 77380 | 30.1613 | -95.4706 |  | Pending
Group 2 | St. 26 | 29915 I-45 | Shenandoah | 77381 | 30.1794 | -95.4624 |  | Pending
Group 2 | St. 27 | 5918 FM 1488 | Magnolia | 77354 | 30.2247 | -95.5578 |  | Pending
Group 3 | St. 12 | 14421 Hwy 105 E | Cut-N-Shoot | 77306 | 30.3324 | -95.3489 |  | Pending
Group 3 | St. 30 | 21084 Loop 494 | New Caney | 77357 | 30.1404 | -95.2166 |  | Pending
Group 3 | St. 31 | 14809 First St | Splendora | 77372 | 30.2292 | -95.1645 |  | Pending
Group 3 | St. 32 | 14596 FM 1314 | Conroe | 77302 | 30.2399 | -95.3819 |  | Pending
Group 3 | St. 33 | 16723 FM 2090 | Conroe | 77306 | 30.2564 | -95.3157 |  | Pending
Group 3 | St. 34 | 23550 Loop 494 | Porter | 77365 | 30.1058 | -95.2291 |  | Pending
Group 3 | St. 35 | 20515 FM 1314 | Porter | 77365 | 30.1527 | -95.3036 |  | Pending
Group 4 | St. 40 | 14575 FM 1488 | Magnolia | 77354 | 30.2278 | -95.6934 |  | Pending
Group 4 | St. 41 | 12527 Patridge Cir | Pinehurst | 77362 | 30.1491 | -95.6624 |  | Pending
Group 4 | St. 42 | 26555 Nichols Sawmill Rd | Magnolia | 77355 | 30.1333 | -95.7534 |  | Pending
Group 4 | St. 43 | 18960 Freeport Dr | Montgomery | 77356 | 30.3861 | -95.6619 |  | Pending
Group 4 | St. 44 | 18294 FM 1097 | Montgomery | 77356 | 30.4376 | -95.6367 |  | Pending
Group 4 | St. 46 | 2615 Woodforest Pkwy N | Montgomery | 77316 | 30.2826 | -95.5674 |  | Pending
Group 4 | St. 47 | 19530 Keenan Cut-Off Rd | Montgomery | 77316 | 30.3253 | -95.6678 |  | Pending

## Tower Sites
MCHD — Tower Sites (Device Upgrade — Not Mapped)
7 Tower sites for device upgrades — visit independently from station groups
# | Tower Name | Address | City | ZIP | Notes / Contacts | Upgrade Status | Date Completed
1 | Conroe Service Center Tower | 1400 South Loop 336 West | Conroe | 77304 | -Data drop needed for LSP, 1501 to be reused from Service Bldg, install enclosure,install batteries, Program and test | Pending
2 | East County / Splendora Tower | 14809 First St | Splendora | 77372 | -Change carder to KEYPAD, install battery, One grounding lug install, program and test | Partial
3 | Thompson Road Tower | 12370 Thompson Rd | Willis | 77318 | -Change carder to KEYPAD, install battery, program and test | Partial
4 | Robinson Rd Tower | 27906 Robinson Rd | Spring | 77386 | -Change card readers to KEYPADS (Bldg1/2), install batteries (Bldg 1/2), install MP1501 board(Bldg 2), , program and test | Partial
5 | Magnolia Tower | 14575 FM 1488 | Magnolia | 77354 | -Change card readers to KEYPADS (Bldg1/2), install batteries (Bldg 1/2), install MP1501 board(Bldg 2), program and test | Partial
6 | Grangerland Tower | 13885 Grangerland Rd | Conroe | 77306 | -Panel needs power, change card reader to KEYPAD, install batteries, program and test | Partial
7 | Conroe Service Tower | 401 Sgt Ed Holcomb Blvd N | Conroe | 77304 | -Data drop needed for LSP, MR52 needed, install crashdoor/run composite to Pedestrian Gate, Change readers to KEYPADS,install batteries, Program and test | Partial
Total: 7 Tower Sites |  | 0 of 7 Completed

## Controller Inventory
MCHD — Controller Inventory & Upgrade Status
Source: Controllers ¦ Settings Report · Date: 8/21/2025 · SSP/D2 = 1502 board installed · DController = Needs 1502 replacement
Phys. Addr | Site / Description | Controller Type | IP Address | Firmware | Serial Number | Action Required | Notes
1 | Conroe Service Center Tower | SSP/D2 | 10.1.105.65 | 1.291 | 47825 | Has 1502 — No Action Needed | 1502 Board (SSP/D2)
2 | EMS 10 | SSP/D2 | 10.1.10.30 | 1.291 | 31843 | Has 1502 — No Action Needed | 1502 Board (SSP/D2)
3 | East Tower | SSP/D2 | 10.1.179.34 | 1.294 | 1043654 | Has 1502 — No Action Needed | 1502 Board (SSP/D2)
4 | EMS 32 | SSP/D2 | 10.1.32.40 | 1.291 | 21284 | Has 1502 — No Action Needed | 1502 Board (SSP/D2)
5 | Admin Radio Shelter | SSP/D2 | 10.1.243.200 | 1.291 | 88640 | Has 1502 — No Action Needed | 1502 Board (SSP/D2)
6 | EMS 20 | SSP/D2 | 10.1.20.45 | 1.294 | 1005320 | Has 1502 — No Action Needed | 1502 Board (SSP/D2)
7 | Administration 1st Floor | SSP/D2 | 10.1.243.100 | 1.291 | 31875 | Has 1502 — No Action Needed | 1502 Board (SSP/D2)
8 | Administration 2nd Floor | SSP/D2 | 10.1.243.101 | 1.291 | 31876 | Has 1502 — No Action Needed | 1502 Board (SSP/D2)
9 | Administration 3rd Floor | SSP/D2 | 10.1.243.102 | 1.291 | 31873 | Has 1502 — No Action Needed | 1502 Board (SSP/D2)
10 | EMS-11 Service Center | SSP/D2 | 10.1.243.103 | 1.291 | 31874 | Has 1502 — No Action Needed | 1502 Board (SSP/D2)
11 | EMS 30 | SSP/D2 | 10.1.30.30 | 1.294 | 1005321 | Has 1502 — No Action Needed | 1502 Board (SSP/D2)
12 | EMS 31 | SSP/D2 | 10.1.31.30 | 1.291 | 32643 | Has 1502 — No Action Needed | 1502 Board (SSP/D2)
13 | EMS 40 | DController | 10.1.40.25 | 1.188 | 41173 | NEEDS REPLACEMENT → 1502 | Replace with 1502
15 | EMS 14 | SSP/D2 | 10.1.14.30 | 1.291 | 68815 | Has 1502 — No Action Needed | 1502 Board (SSP/D2)
16 | EMS 45 | SSP/D2 | 10.1.45.30 | 1.291 | 68822 | Has 1502 — No Action Needed | 1502 Board (SSP/D2)
17 | Thompson Road Tower | DController | 10.1.175.38 | 1.291 | 41159 | NEEDS REPLACEMENT → 1502 | Replace with MP 1502
18 | Robinson Rd Tower | DController | 10.1.178.38 | 1.291 | 41172 | NEEDS REPLACEMENT → 1502 | Replace with MP1502
19 | Magnolia Tower | DController | 10.1.177.38 | 1.291 | 41167 | NEEDS REPLACEMENT → 1502 | Replace with MP1502
37 | EMS 23 | DController | 10.1.23.200 | 1.294 | 104325 | NEEDS REPLACEMENT → 1502 | Replace with MP1502
21 | Controlled Substance Storage | PIM400-1501 | 10.1.243.80 | 1.291 | 34852 | Review — Other Type | PIM400-1501 (Review)
22 | EMS 43 | DController | 10.1.43.38 | 1.291 | 8841 | NEEDS REPLACEMENT → 1502 | Replace with 1502
23 | EMS 41.1 | PIM400-1501 | 10.1.41.38 | 1.291 | 62909 | Review — Other Type | PIM400-1501 (Review)
24 | EMS 41.2 | PIM400-1501 | 10.1.41.39 | 1.291 | 62688 | Review — Other Type | PIM400-1501 (Review)
30 | EMS 15 | SSP-LX | 10.1.15.30 | 1.294 | 1006413 | Review — Other Type | SSP-LX (Review)
26 | Grangerland Tower | DController | 10.1.176.38 | 1.291 | 1028810 | NEEDS REPLACEMENT → 1502 | Replace with 1502
27 | EMS 27 | SSP/D2 | 10.1.27.40 | 1.294 | 631 | Has 1502 — No Action Needed | 1502 Board (SSP/D2)
28 | Admin 1st Floor PIM 1501 Rm 113 | PIM400-1501 | 10.1.243.55 | 1.294 | 1027727 | Review — Other Type | PIM400-1501 (Review)
29 | Magnolia Tower B2 | SSP/D2 | 10.1.40.37 | 1.143 | 41271 | Has 1502 — No Action Needed | 1502 Board (SSP/D2)
31 | EMS 21 | DController | 10.1.21.200 | 1.294 | 57200 | NEEDS REPLACEMENT → 1502 | Replace with 1502
32 | EMS 22 | DController | 10.1.22.200 | 1.294 | 57201 | NEEDS REPLACEMENT → 1502 | Replace with 1502
33 | EMS 12 | SSP/D2 | 10.1.12.200 | 1.294 | 84900 | Has 1502 — No Action Needed | 1502 Board (SSP/D2)
34 | EMS 34 | DController | 10.1.34.200 | 1.294 | 87648 | NEEDS REPLACEMENT → 1502 | Replace with 1502
35 | EMS 42 Medical Supply Closet | DController | 10.1.42.200 | 1.300 | 104478 | NEEDS REPLACEMENT → 1502 | Replace with 1502
36 | Service Center Radio Office | SSP/D2 | 10.1.243.202 | 1.294 | 110213 | Has 1502 — No Action Needed | 1502 Board (SSP/D2)
38 | EMS 25 | DController | 10.1.25.200 | 1.294 | 104343 | NEEDS REPLACEMENT → 1502 | Replace with 1502
39 | EMS 13 | DController | 10.1.13.200 | 1.302 | 112446 | NEEDS REPLACEMENT → 1502 | Replace with 1502
40 | EMS 33 | DController | 10.1.33.200 | 1.304 | 127017 | NEEDS REPLACEMENT → 1502 | Replace with 1502
153 | ZZTesting 1502 | SSP/D2 | 1.1.1.1 | 0.0 | 0 | Has 1502 — No Action Needed | 1502 Board (SSP/D2)
41 | EMS 20 Supervisor Office | SSP/D2 | 10.1.20.112 | 1.305 | 205108 | Has 1502 — No Action Needed | 1502 Board (SSP/D2)
42 | EMS Station 41 Medical Supply RM | DController | 10.1.41.25 | 2.20 | 807515 | NEEDS REPLACEMENT → 1502 | Replace with 1502

## Has 1502 (SSP-D2)
Controllers with 1502 Board Already Installed (20 units)
SSP/D2 type — 1502 controller board is already installed. No hardware replacement needed.
# | Phys. Addr | Site / Description | IP Address | Firmware | Serial Number | Status
1 | 1 | Conroe Service Center Tower | 10.1.105.65 | 1.291 | 47825 | ✓ 1502 Installed
2 | 2 | EMS 10 | 10.1.10.30 | 1.291 | 31843 | ✓ 1502 Installed
3 | 3 | East Tower | 10.1.179.34 | 1.294 | 1043654 | ✓ 1502 Installed
4 | 4 | EMS 32 | 10.1.32.40 | 1.291 | 21284 | ✓ 1502 Installed
5 | 5 | Admin Radio Shelter | 10.1.243.200 | 1.291 | 88640 | ✓ 1502 Installed
6 | 6 | EMS 20 | 10.1.20.45 | 1.294 | 1005320 | ✓ 1502 Installed
7 | 7 | Administration 1st Floor | 10.1.243.100 | 1.291 | 31875 | ✓ 1502 Installed
8 | 8 | Administration 2nd Floor | 10.1.243.101 | 1.291 | 31876 | ✓ 1502 Installed
9 | 9 | Administration 3rd Floor | 10.1.243.102 | 1.291 | 31873 | ✓ 1502 Installed
10 | 10 | EMS-11 Service Center | 10.1.243.103 | 1.291 | 31874 | ✓ 1502 Installed
11 | 11 | EMS 30 | 10.1.30.30 | 1.294 | 1005321 | ✓ 1502 Installed
12 | 12 | EMS 31 | 10.1.31.30 | 1.291 | 32643 | ✓ 1502 Installed
13 | 15 | EMS 14 | 10.1.14.30 | 1.291 | 68815 | ✓ 1502 Installed
14 | 16 | EMS 45 | 10.1.45.30 | 1.291 | 68822 | ✓ 1502 Installed
15 | 27 | EMS 27 | 10.1.27.40 | 1.294 | 631 | ✓ 1502 Installed
16 | 29 | Magnolia Tower B2 | 10.1.40.37 | 1.143 | 41271 | ✓ 1502 Installed
17 | 33 | EMS 12 | 10.1.12.200 | 1.294 | 84900 | ✓ 1502 Installed
18 | 36 | Service Center Radio Office | 10.1.243.202 | 1.294 | 110213 | ✓ 1502 Installed
19 | 153 | ZZTesting 1502 | 1.1.1.1 | 0.0 | 0 | ✓ 1502 Installed
20 | 41 | EMS 20 Supervisor Office | 10.1.20.112 | 1.305 | 205108 | ✓ 1502 Installed

## Needs Replacement
Controllers Requiring 1502 Replacement (15 units)
DController type must be swapped out for a 1502 controller board
# | Phys. Addr | Site / Description | IP Address | Firmware | Serial Number | Replacement Status
1 | 13 | EMS 40 | 10.1.40.25 | 1.188 | 41173 | Pending Replacement
2 | 17 | Thompson Road Tower | 10.1.175.38 | 1.291 | 41159 | Pending Replacement
3 | 18 | Robinson Rd Tower | 10.1.178.38 | 1.291 | 41172 | Pending Replacement
4 | 19 | Magnolia Tower | 10.1.177.38 | 1.291 | 41167 | Pending Replacement
5 | 37 | EMS 23 | 10.1.23.200 | 1.294 | 104325 | Pending Replacement
6 | 22 | EMS 43 | 10.1.43.38 | 1.291 | 8841 | Pending Replacement
7 | 26 | Grangerland Tower | 10.1.176.38 | 1.291 | 1028810 | Pending Replacement
8 | 31 | EMS 21 | 10.1.21.200 | 1.294 | 57200 | Pending Replacement
9 | 32 | EMS 22 | 10.1.22.200 | 1.294 | 57201 | Pending Replacement
10 | 34 | EMS 34 | 10.1.34.200 | 1.294 | 87648 | Pending Replacement
11 | 35 | EMS 42 Medical Supply Closet | 10.1.42.200 | 1.300 | 104478 | Pending Replacement
12 | 38 | EMS 25 | 10.1.25.200 | 1.294 | 104343 | Pending Replacement
13 | 39 | EMS 13 | 10.1.13.200 | 1.302 | 112446 | Pending Replacement
14 | 40 | EMS 33 | 10.1.33.200 | 1.304 | 127017 | Pending Replacement
15 | 42 | EMS Station 41 Medical Supply RM | 10.1.41.25 | 2.20 | 807515 | Pending Replacement
Total: 15 units |  | 0 of 15 Replaced

## Other Types — Review
Other Controller Types — Requires Review (5 units)
PIM400-1501 and SSP-LX types — not classified as SSP/D2 or DController. Review to determine if replacement is needed.
# | Phys. Addr | Site / Description | Controller Type | IP Address | Firmware | Serial Number
1 | 21 | Controlled Substance Storage | PIM400-1501 | 10.1.243.80 | 1.291 | 34852
2 | 23 | EMS 41.1 | PIM400-1501 | 10.1.41.38 | 1.291 | 62909
3 | 24 | EMS 41.2 | PIM400-1501 | 10.1.41.39 | 1.291 | 62688
4 | 30 | EMS 15 | SSP-LX | 10.1.15.30 | 1.294 | 1006413
5 | 28 | Admin 1st Floor PIM 1501 Rm 113 | PIM400-1501 | 10.1.243.55 | 1.294 | 1027727